## Sheet1
Week | Start Date | End Date | Task Description | Assigned To | Progress
1 | 2025-06-27 | 2025-07-04 | Team formation & domain finalization | Manan, Krish, Shaurya | A
2 | 2025-07-04 | 2025-07-11 | Factory requirements analysis from all user roles | Manan, Krish, Shaurya |  | A
3 | 2025-07-11 | 2025-07-18 | Finalize features, plan modules, choose tech stack | Manan, Krish, Shaurya |  |  | A
4 | 2025-07-18 | 2025-07-25 | UI wireframe for admin panel, employee module | Krish |  |  |  | a
5 | 2025-07-25 | 2025-08-01 | Build admin panel UI (basic routing, layout) | Krish |  |  |  |  | a
6 | 2025-08-01 | 2025-08-08 | Add/remove employee logic, DB integration | Manan, Krish | [5 empty] | a
7 | 2025-08-08 | 2025-08-15 | Employee logging module (form + DB entry) | Shaurya | [6 empty] | a
8 | 2025-08-15 | 2025-08-22 | Transporter and customer log modules | Shaurya | [7 empty] | a
9 | 2025-08-22 | 2025-08-29 | Implement Firebase Auth (OTP/QR-based) | Manan | [8 empty] | a
10 | 2025-08-29 | 2025-09-05 | Firestore integration for logs | Krish, Shaurya | [9 empty] | a
11 | 2025-09-05 | 2025-09-12 | Real-time delivery tracking with notifications | Manan | [10 empty] | a
12 | 2025-09-12 | 2025-09-19 | Admin analytics (charts, filters, monitoring) | Krish | [11 empty] | a
13 | 2025-09-19 | 2025-09-26 | Testing core functionalities | Manan, Shaurya | [12 empty] | a
14 | 2025-09-26 | 2025-10-03 | Mobile/web responsiveness, performance optimization | Manan, Krish | [13 empty] | a
15 | 2025-10-03 | 2025-10-10 | Final report, documentation & project submission | All Members | [14 empty] | a